## Sheet1
Defect ID | Defect RCA | Defect Type | Description | Detected By | Detected in Cycle | Detected on Date | Environment | Func Area | Reproducible | Root Cause Description | Severity | Status | Summary | System
93 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S034_C002 System Parameter Configuration_ClearResult Run: Run_12-31_12-1-38 Test Parameters: Step: 20 Description: Input search conditions at random and Click 'Search' button. Expected: System lists corresponding query results according to seasch conditions. Actual: Network error is displayed Run Step[3009] : 20 | shameer | UAT2 | 2018-12-31 | QA | Apps Integration | Y | Root Cause Description: interceptor intercepted special characters Resolution Details: changed interception rules ok | 3-Medium | Closed | For special character system show 'Network Error | PPMS
94 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S034_C004 System Parameter Configuration_EditDict Run: Run_12-31_12-33-0 Test Parameters: Run[566] : Run_12-31_12-33-0 Defect description. 1. Dictionary name and Dictionary code in the main screen and Edit/Add screen should be in the same order .2. As per the screen the char length is 2 to 30 char but can enter 51 chars | shameer | UAT2 | 2018-12-31 | QA | Apps Integration | Y | Root Cause Description: Prompting message error Resolution Details: Amended prompting message | 3-Medium | Closed | Character lenght limit is not accurate | PPMS
95 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S034_C005 System Parameter Configuration_DeleteDic Run: Run_12-31_12-57-23 Test Parameters: Step: 20 Description: Select one Dict name and Click “Delete' button. Expected: System delete this Dict Name. Actual: 1. Confirm spell is wrong in the message dialog. 2. Also give the Dictionary Name in the confirmation message dialog. Run Step[3032] : 20 | shameer | UAT2 | 2019-01-02 | QA | Apps Integration | Y | Root Cause Description: Refined requirements Spelling problem Resolution Details: Revised according to the requirements Modified the spelling | 4-Low | Closed | Cosmetic issue (prompt messages or spelling) | PPMS
96 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S034_C006 System Parameter Configuration_View Run: Run_1-2_12-34-51 Test Parameters: Step: 20 Description: Select one Dict name and Click “Type View” button. Expected: System display “dictionary Type List' in the right area of the window. Actual: "showname" column case shoold be like the other columns in the dialog, Show Name Run Step[3041] : 20 | shameer | UAT2 | 2019-01-02 | QA | Apps Integration | Y | Root Cause Description: Display problem Resolution Details: synchronized | 4-Low | Closed | Cosmetic issue (prompt messages or spelling) | PPMS
97 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S034_C007 System Parameter Configuration_AddType Run: Run_1-2_12-46-50 Test Parameters: Step: 10 Description: Login in PPMS and Go to System Parameter Configuration page. Expected: System displays System Parameter Configuration page. Actual: "showname" column case shoold be like the other columns in the dialog, Show Name Run Step[3042] : 10 | shameer | UAT2 | 2019-01-02 | QA | Apps Integration | Y | Root Cause Description: Display problem Resolution Details: synchronized | 4-Low | Closed | Cosmetic issue (prompt messages or spelling) | PPMS
98 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S001_C004 Account opening Run: Run_1-2_13-9-3 Test Parameters: Run[578] : Run_1-2_13-9-3 | YONGHENG | UAT2 | 2019-01-02 | QA | Apps Integration | Y | Root Cause Description: For operational safety, before save information that acquired from EBS, PPMS's Blocker will verify the string. Now Blocker treat character ' as illegal, so the Blocker stop the process of account opening. Resolution Details: Canceled the verification for special character ' ' ' | 2-High | Fixed | Account opening failed | PPMS
99 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S021_C004 Customer Information Query_Exception-4 Run: Run_1-2_14-11-35 Test Parameters: Step: 20 Description: Click [Search] button. Expected: System prompt error message Actual: System prompt wrong error message. 1. Input a street name with * - tampinesst 11*, but the error message prompted to input numbers only. which is not right as premise address will consist of letters, numbers with # and - for unit no (eg.#10-112). 2. Input full address to test for length error - 26 Sin Ming IndEst Sector A #10-112 Sameerror message prompted to enter numbers only. 3. Input numbers - 26 searchresult was found Please see attached screenshot. Run Step[3071] : 20 | RAFIQHABJ | UAT2 | 2019-01-02 | QA | Apps Integration | Y | Root Cause Description: Program restirction for sensitive words Resolution Details: Change program to allow common special characters in address | 3-Medium | Fixed | Error message incorrect | PPMS
100 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S034_C009 System Parameter Configuration_DeleteType Run: Run_1-2_14-48-45 Test Parameters: Step: 30 Description: Select one Type name and Click “Delete” button. Expected: System show success message. Actual: Need to give the item name in the Message window-> Confirm to delete [----------] type Run Step[3079] : 30 | shameer | UAT2 | 2019-01-02 | QA | Apps Integration | Y | Root Cause Description: Display problem Resolution Details: synchronized | 4-Low | Closed | Need to give the item name in the Message window | PPMS
101 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S042_C002 Holiday Management_Add-1 Run: Run_1-3_11-22-45 Test Parameters: Step: 30 Description: Fill the correct information of the new Holiday in the windows and Click 'Submit' Button. ( Holiday Name/Start Day/End Day/Description) Expected: System prompt success message. Actual: Add holiday dialog box should contain [holiday name] and ok button to close the dialog Run Step[3171] : 30 | shameer | UAT2 | 2019-01-03 | QA | Apps Integration | Y | Root Cause Description: Display problem Resolution Details: synchronized | 4-Low | Closed | Holiday dialog box should contain [holiday name] and ok button to close the dialog | PPMS
102 | 01 Code Change | 03 Query | Test Set: UAT2 Test: PPMS_S041_C001 Terminal Management_Search Run: Run_1-3_15-33-44 Test Parameters: Run[625] : Run_1-3_15-33-44 Dropdown list under Center Name is not shown correctly | chinhiong | UAT2 | 2019-01-03 | QA | Apps Integration | Y | Root Cause Description: Display problem Resolution Details: Extend display character size. | 4-Low | Fixed | Dropdown list under center name is not shown correctly | PPMS
103 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S033_C004 Email Template Configuration_Edit Run: Run_1-3_20-4-11 Test Parameters: Step: 30 Description: Fill the correct information of the template in the windows and Click 'Submit' Button. (E.g.: Select one template from the 'Email Type' droplists;Input Subject; fill 2 in 'Send times'; Choose Status as “enable” or “disable“; Choose 'Start Time' and 'End Time'; Fill 'Test' in Content text box.) Expected: System prompt success message. Actual: Error "Sensitive words found" message Run Step[3281] : 30 | haslina | UAT2 | 2019-01-03 | QA | Apps Integration | Y | Root Cause Description: Program restriction for sensitive words Resolution Details: Change program to allow common special characters in email template | 3-Medium | Fixed | Error "Senstive words found" message prompt. No changes made to the content. Only change from enable to disable. | PPMS
104 | 02 Config Change | 04 Performance | Test Set: UAT2 Test: PPMS_S011_C005 SP Reverse-1 Run: Run_1-4_11-9-44 Test Parameters: Step: 80 Description: PPMS updates the account balance. Expected: PPMS updates the account balance. Actual: Result: Fail - To remove "REVERSED" and to rename "REVERSE" to "REVERSE (C)" AND "REVERSE (X)" where "REVERSE (C)" is the status before the reversal done and "REVERSE (X)" is afterthe reversal done. Run Step[3301] : 80 | YONGHENG | UAT2 | 2019-01-04 | QA | Apps Integration | Y | Root Cause Description: Description changed as user requirement Resolution Details: Config changed | 4-Low | Fixed | Renaming of "REVERSE" status | PPMS
105 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S011_C005 SP Reverse-1 Run: Run_1-4_11-9-44 Test Parameters: Step: 70 Description: Click [Confirm] button Expected: System prompt reverse successfully. Actual: Result: Fail - Receipt should reflect as non-duplicate for first print Run Step[3300] : 70 | YONGHENG | UAT2 | 2019-01-04 | QA | Apps Integration | Y | Root Cause Description: Print times counting mass up with Top-up receipt print times Resolution Details: Code changed. | 4-Low | Fixed | Receipt should reflect as non-duplicate for first print | PPMS
106 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S006_C004 Print Top-up Card_ClearResult Run: Run_1-4_17-24-23 Test Parameters: Step: 30 Description: Click [Clear] button. Expected: Filter conditions will be cleared and previous search result will not be cleared Actual: 1. Filter conditions & previous search results are cleared. 2. Error message of "No record found" is prompted. 3. For the search result is the Customer Salutation portion required? It is better to have thecustomer name instead of the salutation. Please amend. Run Step[3347] : 30 | RAFIQHABJ | UAT2 | 2019-01-04 | QA | Apps Integration | Y | Root Cause Description: Issue about logic adjustment Resolution Details: Change logic of CLEAR function | 3-Medium | Fixed | Error message prompted after clicking [Clear] button | PPMS
107 |  | 01 Functional | Test Set: UAT2 Test: PPMS_S010_C004 Customer top-up record query_Exception-2 Run: Run_1-4_15-39-7 Test Parameters: Step: 20 Description: Click [Search] button. Expected: System prompt error message Actual: Failed Reasons: No error message prompt - "No record found" Run Step[3344] : 20 | ANGGUATCHOO | UAT2 | 2019-01-07 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 4-Low | Rejected | No error message prompt | PPMS
108 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S010_C010 Customer top-up record query-6 Run: Run_1-7_11-28-53 Test Parameters: Step: 20 Description: Click [Search] button. Expected: System search result displays relevant top-up record. Actual: Failed Reasons: Highlighted "Payment mode" column should reflect as "cash, nets, cheque or voucher, etc". Circle in red should only reflect operator transactions. Run Step[3353] : 20 | ANGGUATCHOO | UAT2 | 2019-01-07 | QA | Apps Integration | Y | Root Cause Description: Front-end reading a wrong field in DB Resolution Details: Change SQL in code. | 3-Medium | Fixed | Payment mode column wrong | PPMS
109 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S002_C002 Account activation_Exception-2 Run: Run_1-7_12-34-12 Test Parameters: Run[675] : Run_1-7_12-34-12 | YONGHENG | UAT2 | 2019-01-07 | QA | Apps Integration | Y | Root Cause Description: System doesn't verify the rationality of the date field. Resolution Details: code change | 3-Medium | Fixed | Manual Keying of Date Selection | PPMS
110 |  | 03 Query | Test Set: UAT2 Test: PPMS_S020_C002 Remote Reconnection_Exception-2 Run: Run_1-8_16-32-28 Test Parameters: Step: 20 Description: Input an incomplete account number which less than 11 digits and Click [Search] button. Expected: System lists all the remote reconnection record with the account number inludes the digits input in the search conditions. Actual: Entered "89" and got error message to key in 10 -11 valid characters Run Step[3494] : 20 | JORDANLYM | UAT2 | 2019-01-08 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 3-Medium | Rejected | Entered "89" and got error message to key in 10 - 11 valid characters | PPMS
111 | 01 Code Change | 03 Query | Test Set: UAT2 Test: PPMS_S004_C002 Credit Transfer Apply_Exception-2 Run: Run_1-8_16-10-36 Test Parameters: Run[707] : Run_1-8_16-10-36 | YONGHENG | UAT2 | 2019-01-08 | QA | Apps Integration | Y | Root Cause Description: Refinde requirements Resolution Details: Code change | 4-Low | Fixed | Refining of information in header | PPMS
112 | 10 Others | 03 Query | Test Set: UAT2 Test: PPMS_S020_C003 Remote Reconnection-1 Run: Run_1-8_16-37-5 Test Parameters: Step: 30 Description: Input search conditions at random and Click 'Clear' button. Expected: Filter conditions will be cleared and previous search result will not be cleared Actual: Full list of reconnection log appears when i click"Clear" Run Step[3497] : 30 | JORDANLYM | UAT2 | 2019-01-08 | QA | Apps Integration | Y | Root Cause Description: Wrong code version Resolution Details: Change to correct code version | 3-Medium | Fixed | Full list of reconnection log appears when i click "Clear" | PPMS
113 | 10 Others | 01 Functional | Test Set: UAT2 Test: PPMS_S004_C004 Credit Transfer Apply_ClearResult Run: Run_1-8_17-7-33 Test Parameters: Step: 30 Description: Click [Clear] Expected: Actual: Clear button is not functioning. Under Source Account : - When clicking the [Clear] button, the account number in source account iscleared however the records are populated under Target account section. Under Target Account : - When clicking the [Clear] button, the account number in target account iscleared however additional records are populated under Target account section. Run Step[3504] : 30 | RAFIQHABJ | UAT2 | 2019-01-08 | QA | Apps Integration | Y | Root Cause Description: Wrong code version Resolution Details: Change to correct code version | 3-Medium | Fixed | Clear button is not functioning | PPMS
114 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S016_C003 Day End Reconciliation Run: Run_1-9_15-33-29 Test Parameters: Step: 40 Description: Click [Export] button to export the query result as excel file. Expected: System popup windows to ask for the path to store the generated excel file. Actual: Result :Failed Reason : File cannot be Exported Run Step[3529] : 40 | FAUZLINBS | UAT2 | 2019-01-09 | QA | Apps Integration | Y | Root Cause Description: Exception occurred during file export Resolution Details: code change | 3-Medium | Fixed | Cannot export file | PPMS
115 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S046_C004 Detailed Transaction Report_Filter Run: Run_1-9_16-16-50 Test Parameters: Step: 40 Description: Selecting filter conditons and click 'Filter' button. ( 'Transaction Type', ”Counter ID“ & ”Operator ID“ ) Expected: System lists the records filtered by filter conditions. Actual: Result : Failed Data reflected as all operator ids instead of only 1 operator id. Eg should only reflect filtered transactions by operator id indicated instead of all operator ids Run Step[3545] : 40 | FAUZLINBS | UAT2 | 2019-01-09 | QA | Apps Integration | Y | Root Cause Description: Filter condition 'operatoer id' doesn't work in program. Resolution Details: Code change | 4-Low | Fixed | Data reflected as all operator ids instead of only 1 operator id | PPMS
116 |  | 04 Performance | Test Set: UAT2 Test: PPMS_S013_C003 Refund Approval_Exception-3 Run: Run_1-10_12-45-56 Test Parameters: Run[734] : Run_1-10_12-45-56 | YONGHENG | UAT2 | 2019-01-10 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 4-Low | Rejected | "Confirn" button is hidden | PPMS
117 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S013_C003 Refund Approval_Exception-3 Run: Run_1-10_12-45-56 Test Parameters: Run[734] : Run_1-10_12-45-56 | YONGHENG | UAT2 | 2019-01-10 | QA | Apps Integration | Y | Root Cause Description: Program display telephone number instead of mobile phone number. Resolution Details: Code change | 3-Medium | Fixed | Contact Number is not reflected | PPMS
118 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S013_C005 Refund Approval-2 Run: Run_1-10_17-21-17 Test Parameters: Run[754] : Run_1-10_17-21-17 | YONGHENG | UAT2 | 2019-01-10 | QA | Apps Integration | Y | Root Cause Description: Wrong prompt message content Resolution Details: Code change | 4-Low | Fixed | To rephrase "Refund approval succeed" with "Refund has been declined" for refund declined case and "Refund has been approved" for refund approved | PPMS
119 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S006_C001 Print Top-up Card_Exception-1 Run: Run_1-10_17-29-15 Test Parameters: Step: 20 Description: Click [Search] button. Expected: System prompt error message Actual: Result: Failed Result not as expected. when input an inactivated account no,system should prompt error msg and print top up should NOT be allowed. Run Step[3634] : 20 | FAUZLINBS | UAT2 | 2019-01-10 | QA | Apps Integration | Y | Root Cause Description: Account with status except 'Closed' and 'Cancelled' should be allowed to print top-up card. Resolution Details: Code change | 3-Medium | Fixed | test on inactivated acct no,system should prompt error or no record found | PPMS
120 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S006_C003 Print Top-up Card-2 Run: Run_1-11_12-11-23 Test Parameters: Step: 30 Description: Click print receipt button Expected: System displays the information of receipt. Actual: Result : Failed reason: Receipt printed wrong location.User selected MLT for logged in but receipt printed as HDB.End day report affected. Run Step[3666] : 30 | FAUZLINBS | UAT2 | 2019-01-11 | QA | Apps Integration | Y | Root Cause Description: Progrem get wrong location Resolution Details: Code change | 4-Low | Fixed | Wrong location printed in receipt.Did not tally with processing ctr | PPMS
121 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S005_C004 Credit Transfer Approval-1 Run: Run_1-11_13-59-33 Test Parameters: Run[771] : Run_1-11_13-59-33 | YONGHENG | UAT2 | 2019-01-11 | QA | Apps Integration | Y | Root Cause Description: Program dosen't truncate the decimal of amount when generating SMS record. Resolution Details: Code change | 4-Low | Fixed | SMS - Credit balance to be limited to 2 decmal place | PPMS
122 |  | 04 Performance | Test Set: UAT2 Test: PPMS_S005_C004 Credit Transfer Approval-1 Run: Run_1-11_13-59-33 Test Parameters: Step: 40 Description: Click [Confirm] button, and agree transfer request. Expected: System prompt transfer approval successful and ApprStatus of the record changed. Actual: Result: Pass Run Step[3681] : 40 | YONGHENG | UAT2 | 2019-01-11 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 4-Low | Rejected | Records should remain at current page after execution | PPMS
123 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S058_C001 Remote Control Report _Query-1 Run: Run_1-4_19-33-19 Test Parameters: Step: 20 Description: In summary information page input an illegal search conditions and Click [Search] button. (Wrong batch range e.g.: the date after current day) Expected: System prompt error message and show blank reocords. Actual: Unable to select date after current day. Error message prompt and show no records. Run Step[3349] : 20 | haslina | UAT2 | 2019-01-13 | QA | Apps Integration | Y | Root Cause Description: No restrictions in program for selecting Resolution Details: Code change | 3-Medium | Fixed | Able to select future batch range. | PPMS
124 |  | 01 Functional | Test Set: UAT2 Test: PPMS_S058_C006 Remote Control Report_Export-2 Run: Run_1-13_13-17-23 Test Parameters: Step: 40 Description: Select the path and click 'OK' button. Expected: System prompt success message. Actual: System never prompt success message Run Step[3764] : 40 | haslina | UAT2 | 2019-01-13 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 4-Low | Rejected | System did not prompt success message after generated excel file is save | PPMS
125 |  | 01 Functional | Test Set: UAT2 Test: PPMS_S045_C004 Day End Reconciliation Report_Filter Run: Run_1-14_14-26-50 Test Parameters: Step: 40 Description: Selecting filter conditons and click 'Filter' button. ('payment mode', 'Transaction Type', ”Counter ID“ & ”Operator ID“ ) Expected: System display the corresponding result. Actual: Result : Failed Reason: Interface no filter condition for counter ID and page view cannot see the whole filtered data such as operator id (cant see if system pull out correct data unlessexport format) Run Step[3790] : 40 | FAUZLINBS | UAT2 | 2019-01-14 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 4-Low | Rejected | System did not display corresponding result | PPMS
126 | 02 Config Change | 01 Functional | Test Set: UAT2 Test: PPMS_S047_C001 Summary Collection Report_Query Run: Run_1-14_15-35-14 Test Parameters: Step: 20 Description: Input correct search conditions and Click [Search] button. (Transaction date /Center/Counter/Query Type/Transaction date + Center/ ...etc.) Note:'+” means “Complex query”. Expected: System displays the corresponding query results base on the search conditions. Actual: Result : Failed Result was not as expected Reason: System displays the corresponding query results base on the search conditions.-Passed Payment mode reflect 02,03 need to remove if not necessary Run Step[3816] : 20 | FAUZLINBS | UAT2 | 2019-01-14 | QA | Apps Integration | Y | Root Cause Description: Credit cardn and debit card no longer as payment mode Resolution Details: Remove the relative parameters in system | 4-Low | Fixed | Payment mode reflect 02,03 need to remove if not necessary | PPMS
127 |  | 01 Functional | Test Set: UAT2 Test: PPMS_S023_C003 Credit Update Record Query_Exception-3 Run: Run_1-14_21-1-10 Test Parameters: Step: 10 Description: Manually input an incorrect meter number (ex, length error, illegal character, etc). Expected: Filling the relevant information Actual: No meter number field Run Step[3919] : 10 | haslina | UAT2 | 2019-01-14 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 3-Medium | Rejected | Missing meter number field | PPMS
128 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S006_C003 Print Top-up Card-2 Run: Run_1-15_13-53-16 Test Parameters: Step: 30 Description: Click print receipt button Expected: System displays the information of receipt. Actual: Result : Failed result not expected Reason: 1)wrong location printed in receipt with affect end of day report- Passed 2) receipt should print only replacement fee only as $5 should not reflect credit another $5 to PPMS- Failed Run Step[3928] : 30 | FAUZLINBS | UAT2 | 2019-01-15 | QA | Apps Integration | Y | Root Cause Description: Program did not check the times of top-up card print Resolution Details: Code change | 4-Low | Fixed | Replacement card with fee but receipt printed credited $5 into PPMS also | PPMS
129 | 01 Code Change | 04 Performance | Test Set: UAT2 Test: PPMS_S003_C003 Account closing-1 Run: Run_1-14_15-13-9 Test Parameters: Run[809] : Run_1-14_15-13-9 | YONGHENG | UAT2 | 2019-01-15 | QA | Apps Integration | Y | Root Cause Description: Cosmetic issue. Resolution Details: Code change | 3-Medium | Fixed | Send times not reflected and to rephrase "Suceed" with "Successful" and "Unsuccessful" | PPMS
130 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S051_C001 RefundReport_Query-1 Run: Run_1-15_16-8-21 Test Parameters: Step: 20 Description: In summary information page input an illegalsearch conditions and Click [Search] button.(Wrong batch range e.g.: the date aftercurrent day) Expected: System prompt error message and showblank reocords. Actual: Failed. Under Date section : Able to select futuredate Under Query Type Section : Daily, canselect tomorrow Date. Under Query Type Section : Monthly, canselect later Months. Under Query Type Section : Yearly, canselect future Years. By default should not allow to select futuredate, month or year even though errormessage is prompted. Run Step[3936] : 20 | RAFIQHABJ | UAT2 | 2019-01-15 | QA | Apps Integration | Y | Root Cause Description: System has no restrictions on selecting future date. Resolution Details: Code change | 4-Low | Fixed | Under Date section able to select future date but error message prompted. | PPMS
131 | 01 Code Change | 03 Query | Test Set: UAT2 Test: PPMS_S043_C001 Account Opening Report_Query Run: Run_1-15_15-50-57 Test Parameters: Step: 30 Description: Input incorrect search conditions. (Wrong date range e.g.: From 25/10/2018 to 20/10/2018/ or the date after current day) Expected: System show error message and show blank reocords. Actual: Result: Pass Run Step[3932] : 30 | YONGHENG | UAT2 | 2019-01-15 | QA | Apps Integration | Y | Root Cause Description: Cosmetic issue and refined requirements. Resolution Details: Code change | 4-Low | Fixed | To rename "Address" as "Premise Address" and to remove "Post Code" column & To include additional search field "Account Opening Date" | PPMS
132 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S057_C003 No Deduction Report Run: Run_1-15_20-42-5 Test Parameters: Step: 20 Description: In summary information page, input correct search conditions and Click [Search] button. Expected: System display the corresponding query result. Actual: No Deduction Days>=16 , does not flag those account = 16 days only flag out > 16 days Run Step[3961] : 20 | haslina | UAT2 | 2019-01-15 | QA | Apps Integration | Y | Root Cause Description: Incomplete processiong logic in program Resolution Details: Code Change | 3-Medium | Fixed | No Deduction Days>=16 , does not flag those account = 16 days only flag out > 16 days | PPMS
133 |  | 03 Query | Test Set: UAT2 Test: PPMS_S050_C002 Cancellation Report_Query-2 Run: Run_1-16_13-36-20 Test Parameters: Step: 20 Description: Inpute incorrect search conditions. (Wrong date range e.g.: From 25/10/2018 to 20/10/2018/ or the date after current day) Expected: System show error message and show blank reocords. Actual: Result : Failed Result not as expected. Reason : Interface do not have date range. Should have filter by Daily,Monthly,Yearly and should have Date range From and To as filter conditions for users. Run Step[4009] : 20 | FAUZLINBS | UAT2 | 2019-01-16 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 4-Low | Rejected | Date range not available in interface | PPMS
134 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S053_C003 Transaction Report_Datalink Run: Run_1-16_17-5-38 Test Parameters: Run[883] : Run_1-16_17-5-38 | judychua | UAT2 | 2019-01-16 | QA | Apps Integration | Y | Root Cause Description: Search result rectified as user required. Resolution Details: Code for displaying changed. | 3-Medium | Fixed | Total records does not tally when click the no, of transaction- Please refer to screenshots_S053_C003 attached | PPMS
135 |  | 01 Functional | Test Set: UAT2 Test: PPMS_S051_C006 Refund Report_Clear-2 Run: Run_1-16_17-6-40 Test Parameters: Step: 40 Description: Select filter conditions and Click 'Filter' button. Expected: System lists the records filtered by conditions. Actual: For Daily Report, under the selected filter conditions, whereby there is no record to display, should prompt error message. For Monthly Report, under the selected filter conditions, the filtered conditions selected did not display and show the last record. Run Step[4066] : 40 | RAFIQHABJ | UAT2 | 2019-01-16 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 3-Medium | Rejected | Filter conditions did not display | PPMS
136 |  | 01 Functional | Test Set: UAT2 Test: PPMS_S052_C005 Credit Transfer Report_Clear-2 Run: Run_1-16_17-27-53 Test Parameters: Run[886] : Run_1-16_17-27-53 | YONGHENG | UAT2 | 2019-01-16 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 3-Medium | Rejected | Filter button not available | PPMS
137 |  | 01 Functional | Test Set: UAT2 Test: PPMS_S058_C005 Remote Control Report_Clear-2 Run: Run_1-13_13-7-56 Test Parameters: Step: 40 Description: Select filter conditions and Click 'Filter' button. Expected: System lists the records filtered by conditions. Actual: No filter button and no filter condition Run Step[3759] : 40 | haslina | UAT2 | 2019-01-17 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 3-Medium | Rejected | No filter condition nd no filter button in the detailed information | PPMS
138 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S048_C008 Top up Card Issuance Report_Export-2 Run: Run_1-17_15-25-3 Test Parameters: Step: 40 Description: Select the path and click 'OK' button. Expected: System prompt success message. Actual: Result : Failed Result not as expected. reason: Page view should have full view for all Data to be viewed Exported file failed- account status export under coded number instead of word "activated" Run Step[4143] : 40 | FAUZLINBS | UAT2 | 2019-01-17 | QA | Apps Integration | Y | Root Cause Description: SQL statement for data exporting is different with search SQL Resolution Details: SQL changed. | 4-Low | Fixed | Exported file did not filter correctly | PPMS
139 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S078_C002 Arrear Percentage Update Run: Run_1-17_17-20-59 Test Parameters: Step: 30 Description: Click 'Edit' button and select new percentage value Expected: System pops up a new dialog box and only allows update of arrear percentage. Actual: Error message occur Run Step[4148] : 30 | haslina | UAT2 | 2019-01-17 | QA | Apps Integration | Y | Root Cause Description: Wrong processing logic in program Resolution Details: Code change | 3-Medium | Fixed | Error message occur "The current terminal information does not exist (no operation permission), please contact the administrator" | PPMS
140 |  | 01 Functional | Test Set: UAT2 Test: PPMS_S057_C006 No Deduction Report _Export-1 Run: Run_1-15_20-59-4 Test Parameters: Step: 30 Description: Click [Export] button to export the query result as excel file. Expected: System popup windows to ask for the path to store the generated excel file. Actual: Should only export Summary No Deduction Information tab only Run Step[3972] : 30 | haslina | UAT2 | 2019-01-18 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 4-Low | Rejected | Should only export Summary Information tab . Instead system export both tab | PPMS
141 |  | 01 Functional | Test Set: UAT2 Test: PPMS_S057_C007 No Deduction Report_Export-2 Run: Run_1-15_20-59-47 Test Parameters: Step: 30 Description: Click [Export] button to export the query result as excel file. Expected: System popup windows to ask for the path to store the generated excel file. Actual: Should only export Detailed No Deduction Information. Run Step[3976] : 30 | haslina | UAT2 | 2019-01-18 | QA | Apps Integration | Y | Root Cause Description: Resolution Details: | 4-Low | Rejected | Should only export Detailed Information only. Instead system export both in the same file | PPMS
142 | 01 Code Change | 01 Functional | Test Set: UAT2 Test: PPMS_S058_C001 Remote Control Report _Query-1 Run: Run_1-4_19-33-19 Test Parameters: Step: 20 Description: In summary information page input an illegal search conditions and Click [Search] button. (Wrong batch range e.g.: the date after current day) Expected: System prompt error message and show blank reocords. Actual: Able to select future batch range Run Step[3349] : 20 | haslina | UAT2 | 2019-01-18 | QA | Apps Integration | Y | Root Cause Description: 'Calendar Control' used in report interface is not restricted. Resolution Details: Update coding to prohibit manually input | 4-Low | Fixed | The search only display 2 result however nd to scroll down to see another account. There is a large area under the Total Page. | PPMS